## How to use
walkgrid scope (MoSCoW)
Horizon (edit this): the first functional test -- walk a faceted, textured, lit world, hear footsteps with the music, place and remove ground, at 60 fps or better on the owner's PC.
Must -- the horizon fails without it.
Should -- important, but the horizon still works without it.
Could -- nice to have if it's cheap; first to drop.
Won't -- not this horizon (parked, not rejected). The dev pile lives here.
How we use it
1. Before new work starts, it needs a row here. New ideas enter as Could or Won't unless the owner says otherwise.
2. Only the owner sets Must. Claude's suggestions say 'Claude (proposed)' in Decided by until the owner decides.
3. Priority and Status are drop-downs; Summary counts update by themselves.
4. Add a row at the bottom of Scope with the next ID (S040, S041, ...). Example: S040 ¦ Audio ¦ Footstep volume option ¦ Could ¦ Not started ¦ Only if footfalls stay ¦ 10.4 ¦ Owner
5. When a horizon ships, move its Won'ts up for review and set a new horizon above.

## Scope
ID | Area | Item | Priority | Status | Notes / boundary | Design ref | Decided by
W001 | Process | Engine review, prototype outline, foundations | Must | Done | docs/ENGINE_REVIEW.md, PROTOTYPE_OUTLINE.md, FOUNDATIONS.md | Foundations | Owner
W002 | Process | Plan, approve, build, check; say plainly what wasn't verified | Must | In progress | Standing rule, never 'done' | Foundations 1 | Owner
W003 | Engine | Carry the Voxistics engine across intact; take only the Voxistics game layer off (M0) | Must | Done | M0 done, run on the owner's machine 2026-09-25 | Engine review 3 | Owner
W004 | Engine | Lots of action without lag: cost scales with what's on screen or changing | Must | In progress | Standing rule, never 'done' | Foundations 4 | Owner
W005 | Engine | 60 fps floor; higher where the machine allows, with no jitter (interpolated rendering) | Must | In progress | Interpolated rendering in M0.12; frame cap only with vsync off | Outline D10 | Owner
W006 | Engine | Working name walkgrid: project, window, save folder | Must | Done | M0.10 | Outline D11 | Owner
W007 | Engine | Layer rule plus tools/check_layers.sh | Must | Done | 0 violations; check_layers.py runs in tests/run.sh | Foundations 2 | Owner
W008 | Engine | Thread model: main thread owns world and graphics; 2 job threads build from copies; version stamps | Must | In progress | jobs.h (M1.4): terrain on job threads with epochs; meshes from M1.5 | Foundations 3 | Owner
W009 | Engine | Fresh walkgrid save format v1 (no Voxistics loaders) | Must | Done | M0.9: worldfile v1 with a game section; Voxistics loaders removed | Foundations 5 | Owner
W010 | Engine | Camera-relative rendering (no jitter far from the start) | Must | Done | M0.13, with a native test | Foundations 4.2 | Owner
W011 | Engine | Budgets per frame shown in F3 | Must | Not started | Numbers are conservative assumptions; tuned only from reports the owner chooses to share | Foundations 4 | Owner
W012 | World | Faceted surface over the existing grid (option A), not cubes, not blobs | Must | In progress | In game from M1.5 (groundmesh.h, world shader); collision and picking in M1.7 | Outline 3 | Owner
W013 | World | Smaller ground triangles near the player without hurting performance | Must | In progress | Detail cut on lumpy materials only; stitched; 308k tris within 96 blocks in the preview | Foundations 4.1 | Owner
W014 | World | Walk around: walk, sprint, crouch, jump, slide on facets | Must | In progress | On facets from M1.7 (collide.h, D39); scripted walks clean; owner to judge the feel (T6) | Outline 5 | Owner
W015 | World | Place and remove ground, one cell at a time, where the crosshair points | Must | In progress | Picking on facets from M1.7; owner to check it lands where aimed (T8) | Outline 5 | Owner
W016 | World | Seeded test landscape: meadow, dirt, stone, sand regions | Should | Done | walkgrid-hills v1 (M1.4, D37): seeded, pinned; pictures docs/pictures/m1_4 | Outline 3 | Claude (proposed)
W017 | Looks | Textures and lighting carried over (sun, shadows, sky, fog, AO, bloom, glow) | Must | Not started | Checklist T4 | Outline D4 | Owner
W018 | Looks | Smooth-filtered textures | Must | In progress | M1.5: smooth (trilinear, 4x anisotropic) at every distance (D38); up close the 32 px art reads blurry: owner to judge | Outline D8 | Owner
W019 | Looks | Natural blending between materials (height-based) | Must | In progress | Built in M1.6 (height layers, 3-material blend in the shader); owner to judge in game (T3) | Outline 4 | Owner
W020 | Looks | Sky light: pits, overhangs and hollows go dark | Should | In progress | Built in M1.6 (column tops, horizon sky light per vertex); owner to judge (T5) | Outline D4 | Claude (proposed)
W021 | Sound | Day-cycle music as in Voxistics | Must | Not started | Checklist T10 | Outline D2 | Owner
W022 | Sound | Footsteps on the beat, by gait and ground material | Must | Not started | Checklist T7. Louder and brighter (D29); still subtle, owner decides the ceiling in M1 step 1.12 (D31) | Outline 5 | Owner
W023 | Sound | Reactive sound effects that don't interfere with the music | Must | Not started | Checklist T9 | Outline D3 | Owner
W024 | Sound | Effects on their own thread, with a voice cap | Should | In progress | Built in M1.1 (own thread, mailbox, 48-voice cap tested); awaiting the owner's Ctrl+F3 report | Outline D3 | Claude (proposed)
W025 | Controls | First person only | Must | Not started |  | Outline D9 | Owner
W026 | Controls | Raw mouse input | Should | Done | M0.14; awaiting the feel check (C5) | Engine review 2.7 | Claude (proposed)
W027 | Controls | Choose materials from the library menu; hotbar kept for now | Should | Not started | Owner (D30): materials are chosen in the library. The hotbar stays as a placeholder, possibly for other GUI later | Decisions D30 | Owner
W028 | Menus | Title, slots, pause, options (look, graphics, display, audio, keys, accessibility), saves | Should | Not started | Carried over; checklist T11 | Outline 7 | Claude (proposed)
W029 | Debug & checks | Screenshot key | Should | In progress | F2; built, awaiting the owner's check on Windows | Foundations 7 | Claude (proposed)
W030 | Debug & checks | MinGW cross-compile and shader check set up here | Should | Done | tools/check_mingw.sh; shader check runs clean | Foundations 7 | Claude (proposed)
W031 | Debug & checks | CPU still-image preview of faceted ground (with triangle counts) | Should | Done | M1.2: tools/facet_preview.sh; pictures in docs/pictures/m1_2 | Foundations 4.1 | Claude (proposed)
W032 | Debug & checks | Release performance check on the owner's PC (Ctrl+F3 report) | Should | Not started | Awaits the owner at each milestone | Foundations 7 | Claude (proposed)
W033 | Docs | New CLAUDE.md, DESIGN.md and DECISIONS.md; Voxistics docs archived | Should | Done | CLAUDE.md and DESIGN.md done; DECISIONS.md done | Foundations 6 | Claude (proposed)
W034 | Docs | Split game.cpp into input, menus, hud | Should | Done | M0.11 | Engine review 2.7 | Claude (proposed)
W035 | Later | Third person and an animated player model | Won't | Parked | If wanted | Outline D9 | Owner
W036 | Later | Death metal music | Won't | Parked | Real instruments are hard to emulate | Outline D2 | Owner
W037 | Later | Action systems: enemies, projectiles, particles, with budgets | Won't | Parked |  | Outline 2 | Owner
W038 | Later | Real terrain generator with caves | Won't | Parked |  | Outline 2 | Owner
W039 | Later | Unsupported ground falls (Voxistics gravity) | Won't | Parked | Revisit after the first test | Outline 7 | Owner
W040 | Later | Covered grass dies back to dirt | Won't | Parked | Revisit after the first test | Outline 7 | Owner
W041 | Later | Plants that turn to face you | Won't | Parked | Revisit after the first test | Outline 7 | Owner
W042 | Later | See-through materials (glass, ice, water) | Won't | Parked |  | Outline 7 | Claude (proposed)
W043 | Later | Colour-vision modes; first-steps tutorial | Won't | Parked | Served Voxistics features; accessibility no longer a standing rule (D24) | Outline 7 | Claude (proposed)
W044 | Later | Gamepad support | Won't | Parked |  | Engine review 2.7 | Claude (proposed)
W045 | Engine | Render only what can be seen; preload what may be seen soon | Must | In progress | Frustum culling exists; hidden-chunk skipping and heading-aware loading in M1 | Foundations 4.3 | Owner
W046 | Engine | Graphics minimum: Direct3D feature level 11.0, shader model 5.0 | Must | Done | M0.16; awaiting the Windows build to confirm D3DCompile accepts SM5 | Decisions D20 | Owner
W047 | Engine | Harmless reads of OS limits only (thread count, video-memory budget); never kept or shown | Must | In progress | Standing rule (D21) | Decisions D21 | Owner
W048 | Engine | No online play, no network code | Must | In progress | Standing rule, never 'done' (D23) | Decisions D23 | Owner
W049 | Sound | Synthesized sound only: no recorded or sampled audio | Must | In progress | Standing rule, never 'done' (D25) | Decisions D25 | Owner
W050 | Menus | Text ready for any language: string table, wider font atlas | Must | Not started | M1 step 0 (D26) | Decisions D26 | Owner
W051 | Process | SOP binding, two tiers; hooks capped and listed | Must | Done | docs/SOP.md; FOUNDATIONS.md 2.1 (D27) | Decisions D27 | Owner
W052 | Looks | Twelve starting materials, chosen on contact sheets | Should | Done | D36, provisional until the owner confirms; docs/pictures/m1_3 | Decisions D36 | Claude (proposed)
Note on H1: Owner = decided by the owner. Claude (proposed) = a suggestion awaiting the owner's call: promote, demote or delete it.

## Summary
Scope at a glance
Counts update from the Scope sheet.
Priority | Done | In progress | Not started | Parked | Total | Done %
Must
Should
Could
Won't
Total
Open Musts (not done)
Proposals awaiting the owner